## BPPShops- Mobile app
|  |  |  | BPPSHOP Mobile App - seller | TC Start Date |  | TC Execution Start Date |  | TEST CASE SUMMARY
| Module Name |  |  | ALL | TC End Date |  | TC Execution End Date |  | PASS |  |  | 0
| Epic |  |  |  | Test Case Developed By | Rifat Tamanna | Browser (tested) | 1 | FAIL |  |  | 0
| Developer Name (TL) |  |  | x | Test Case Reviewed By |  | Performance (tested) | No | WARNING |  |  | 0
| Test Executed by | [7 empty] | TOTAL |  |  | 0
version | Test Case ID/Name | Feature | Test Case Description | Precondition | Test Data | Step Description | Expected Result | Actual | Status | Severity | Priority | Remarks | comment | Retest | Recheck Remark | Execution Date | Dev Status | Actual Time
Common Steps: -->open the BPPSHOPS Mobile app (Seller)
v#1 | TC001 | Seller app logo | "Logo" | BPPSHOP app (Seller) | N/A | --> Login the seller app --> go to home page | BPPShop logo should be present | Logo does not change | FAIL |  |  | Logo
v#1 | TC002 | Seller Log In | Verify "Email ID" field | BPPSHOP app (Seller) | N/A | --> Click on the "Email ID" Field | Input the email ID and phone number also for other apps perspective | Phone number login system should not be access here | WARRING
v#1 | TC003 | Seller Log In | Verify "Password remember option" | BPPSHOP app (Seller) | N/A | --> Input the "Email ID" -->Input the "password" -->click on the "Remember me" option --> click on the "log In" button | It would work properly | As Accepted | PASS
v#1 | TC004 | Seller Log In | "Forget Password" | BPPSHOP app (Seller) | N/A | --> click on the "Forget password" button --> Click on the "Enter email Field" --> Click on the "Send Email" button | should be login with a valid email id for send the codeinto the email id to change the password | The given email id is not valid that's why don't get any mail | FAIL
v#1 | TC005 | "Menu bar" - "Profile" | Verify "My profile" "Shipping Method" | BPPSHOP app (Seller) | N/A
v#1 | TC006 | "Menu bar" - "Profile" | Verify "My profile" to "back button" | BPPSHOP app (Seller) | N/A | -->click on the "Menu bar" from the bottom navbar --> click on the "profile" button --> click on the "top back icon" | It should be redirect the home page or | As Accepted | PASS
v#1 | TC007 | "Menu bar" - "Profile" | Verify "My profile" to "Edit profile" | BPPSHOP app (Seller) | N/A | -->click on the "Menu bar" from the bottom navbar --> click on the "profile" button --> click on the profile "image" for change the image | Change the image properly | As Accepted | PASS |  |  | email id verification
v#1 | TC008 | "Menu bar" - "Profile" | "Edit Profile" "Total products" "Total order" "Days Since Joined" | BPPSHOP app (Seller) | N/A | -->Click on the "Menu bar" -->click on the "Profile " button --> click on the "Edit profile " button | Total countings are changed with the value change | Not as accepted | FAIL |  |  | values cannot change
v#1 | TC009 | "Menu bar" - "Profile" | "Edit profile" "All input fields" | BPPSHOP app (Seller) | N/A | --> Click on the "Menu bar" --> Click on the "Profile" button -->click on the " | Input field should be shown when the keyboard is open | When click on any input field the keyboard would overlap the input field | FAIL |  |  | overlap the input field
v#1 | TC010 | "My Order" | "All order" "View Details" | BPPSHOP app (Seller) | N/A | -->Click on the "My order" --> click on the "View details" button | Button design should be fixed in the screen | Paid button should overlap into the phone screen | FAIL |  |  | Button overlap the screen
v#1 | TC011 | "My order" | "All order" "View Details" | BPPSHOP app (Seller) | N/A | -->Click on the "My order" --> click on the "View details" button | A location map should be present like the website backend view | location map should not present in seller mobile app | FAIL |  |  | location map
v#1 | TC012 | "My order" | "All order" "View Details" | BPPSHOP app (Seller) | N/A | -->Click on the "My order" --> click on the "View details" button | Why beside the order section (POS) text would present | Why beside the order section (POS) text would present | FAIL |  |  | https://drive.google.com/file/d/1ePZOZgpHRuoHHOx61zMPvuPRCieRg8ZA/view?usp=sharing
v#1 | TC013 | "Menu bar" - "Message" | Verify "Inbox" | BPPSHOP app (Seller) | N/A | -->Click on the "Menu bar" -->Click on the "Message" button -->Click on a any customer name to sent a message -->Send a message into the customer | Messages should be coming in decending format | Messages should be coming in decending format | FAIL |  |  | https://drive.google.com/file/d/1fJX9Yr0J7bSO9ItXXBmTrW0HlGAKb7uS/view?usp=sharing
v#1 | TC014 | "Menu bar" - "Message" | Verify "Message Notification to send the seller" | BPPSHOP app (Seller) | N/A | -->Click on the "Menu bar" -->Click on the "Message" button -->Click on a any customer name to sent a message -->Send a message into the customer | The seller should expect a notification when the customer leaves a message | notification should not sent | FAIL |  |  | https://drive.google.com/file/d/1c8aorR2euWdnApvrQHzo4rkqtuKzT8gR/view?usp=sharing
v#1 | TC015 | "Menu bar" - "Message" | Verify "Message Notification to send the customer" | BPPSHOP app (Seller) | N/A | -->Click on the "Menu bar" -->Click on the "Message" button -->Click on a any customer name to sent a message -->Send a message into the customer | The customer should expect a notification when the seller leaves a message | notification should not sent | FAIL |  |  | https://drive.google.com/file/d/1c8aorR2euWdnApvrQHzo4rkqtuKzT8gR/view?usp=sharing
v#1 | TC016 | "Menu bar" - "Message" | Verify "Message Notification to send the customer" | BPPSHOP app (Seller) | N/A | -->Click on the "Menu bar" -->Click on the "Message" button -->Click on a any customer name to sent a message -->Send a message into the customer | When there is a conversation between seller and customer,the message should be shown immediately | notification should not sent | FAIL
v#1 | TC017 | "Back Button" | verify "Back button" | BPPSHOP app (Seller) | N/A | -->Click on the "Menu bar" -->Click on the "Message" button -->Click on a any customer name to sent a message -->Send a message into the customer | When click on the back button it should be redirect the immediate back page | When click on the back button it would redirect the refund page | FAIL
v#1 | TC018 | "Menu bar" "Wallet" | Verify "Send withdraw request" | BPPSHOP app (Seller) | N/A | -->Click on the "Menu bar" -->Click on the "wallet" button -->click on the "send withdraw request" button | Withdraw request send successfully | Withdraw request send successfully | PASS
v#1 | TC019 | "Menu bar" "Bank info" | verify "Bank Info" | BPPSHOP app (Seller) | N/A | -->Click on the "Menu bar" -->Click on the "Bank info" button -->click on the "edit" button | Edit bank info successfully | Edit bank info successfully | PASS
v#1 | TC020 | "Menu bar" "Add Product" | Verify "Color variant" | BPPSHOP app (Seller) | N/A | -->Click on the "Menu bar" -->Click on the "Add product" button --> Input all the field properly | To see the color variants in dropdown | Color variations are not shown in the dropdown | FAIL |  |  | https://drive.google.com/file/d/1QQQullRDl__N7GdCnSwevIPldX-CJ8Fo/view?usp=sharing
v#1 | TC021 | "Menu bar" "Add Product" | Verify "Youtube link" | BPPSHOP app (Seller) | N/A | -->Click on the "Menu bar" -->Click on the "Add product" button --> Input all the field properly | Without verify the youtube link product should added | Without verify the youtube link product should added | FAIL |  |  | https://drive.google.com/file/d/1Rag43l33eLLf-hiNECpx0h6OQZWzm0Oi/view?usp=sharing
v#1 | TC022 | "Menu bar" "App info version" | Verify "App Info Version" | BPPSHOP app (Seller) | N/A | -->Click on the "Menu bar" -->Click on the "App info version" button | app info version button should be work | app info version button should not work | FAIL